## Sheet1
Task Tracking: Iteration A

Story ID: 1 - Estimate Buyer Savings
Task ID	Task Description	Assigned To:	Estimate	Status
1	Create methods to do calculations based on input	Jack	9
	Story Points: 3 Total Hours:
Story ID: 3 - User Enter's Own Details
Task ID	Task Description		Estimate	Status
1	Create forms for the entry of the users own details	Glenn: Web Interface Kerry: Android Interface	3
2	Update or correct the data computing classes to accept the data	Jack	3
	Story Points: 2 Total Hours:
Story ID: 4 - Electricity Generation 1
Task ID	Task Description		Estimate	Status
1	Write methods for the calculations and an output method	Jack	6
	Story Points: 2 Total Hours:
Story ID: 6 – Data entry form
Task ID	Task Description		Estimate	Status
1	Create forms for data entry	Glenn: Web Interface Kerry: Android Interface	3
	Story Points: 1 Total Hours:
Story ID: 16 – User selects simulation range
Task ID	Task Description		Estimate	Status
1	Update forms to have a space for entry of how much time in years to do the simulation over.	Glenn: Web Interface Kerry: Android Interface	3
	Story Points: 1 Total Hours:

## Sheet2
Iteration A
Work Date	Work Week	Ideal Tasks Remaining (hours)	Actual Tasks Remaining (Hours)	Completed Task Hours: Jack Williams	Completed Task Hours: Kerry Carkson	Completed Task Hours: Lars Gullestrup	Completed Task Hours: Glenn Moir	Total Tasks Hours Completed
	0	27	27					0
Iteration 0.5	1	21	23	3		1		4
Iteration 1	2	14	20			3		3
Iteration 1.5	3	12	20					0
Iteration 2	4	10	20					0
Iteration 2.5	5	7	20					0
Iteration 3	6	4	20					0
Iteration 3.5	7	2	20					0
Iteration 4	8	0	20					0

Iteration A: Burn Down / Week / Remaning Task Hours

## Sheet3
Iteration A					TESTS
Remaining Hours (Ideal)	Hours Taken	Time (Day)	Iteration A / Days / Hours Remaining					PASS	13
27		Tuesday, 28/08					FAIL	0
23		Wednesday, 29/08
19		Thursday, 30/08
15		Friday, 31/08
11		Saturday, 1/09
7		Sunday, 2/09
3		Monday, 3/09
0		Tuesday, 4/09