## Sheet1
Task Tracking: Iteration A
Story ID: 1 - Estimate Buyer Savings
Task ID | Task Description | Assigned To: | Estimate | Status
1 | Create methods to do calculations based on input | Jack | 9
Story Points: 3 Total Hours:
Story ID: 3 - User Enter's Own Details
Task ID | Task Description |  | Estimate | Status
1 | Create forms for the entry of the users own details | Glenn: Web Interface Kerry: Android Interface | 3
2 | Update or correct the data computing classes to accept the data | Jack | 3
Story Points: 2 Total Hours:
Story ID: 4 - Electricity Generation 1
Task ID | Task Description |  | Estimate | Status
1 | Write methods for the calculations and an output method | Jack | 6
Story Points: 2 Total Hours:
Story ID: 6 – Data entry form
Task ID | Task Description |  | Estimate | Status
1 | Create forms for data entry | Glenn: Web Interface Kerry: Android Interface | 3
Story Points: 1 Total Hours:
Story ID: 16 – User selects simulation range
Task ID | Task Description |  | Estimate | Status
1 | Update forms to have a space for entry of how much time in years to do the simulation over. | Glenn: Web Interface Kerry: Android Interface | 3
Story Points: 1 Total Hours:

## Sheet2
Iteration A
Work Date | Work Day | Ideal Tasks Remaining (hours) | Actual Tasks Remaining (Hours) | Completed Task Hours: Jack Williams | Completed Task Hours: Kerry Carkson | Completed Task Hours: Lars Gullestrup | Completed Task Hours: Glenn Moir | Total Tasks Hours Completed
| 0 | 27 | 27 |  |  |  |  | 0
2012-10-28 | 1 | 23 | 27 |  |  |  |  | 0
2012-10-29 | 2 | 19 | 27 |  |  |  |  | 0
2012-10-30 | 3 | 15 | 27 |  |  |  |  | 0
2012-10-31 | 4 | 11 | 27 |  |  |  |  | 0
2012-11-01 | 5 | 7 | 27 |  |  |  |  | 0
2012-11-02 | 6 | 3 | 27 |  |  |  |  | 0
2012-11-03 | 7 | 0 | 27 |  |  |  |  | 0

## Sheet3
Iteration A
Remaining Hours (Ideal) | Hours Taken | Time (Day)
27 |  | 2012-08-28
23 |  | 2012-08-29
19 |  | 2012-08-30
15 |  | 2012-08-31
11 |  | 2012-09-01
7 |  | 2012-09-02
3 |  | 2012-09-03
0 |  | 2012-09-04